## Hawarden RSA Hall
Hawarden RSA Hall
PROP1154 (1154-TOYLI)
| Condition Inspection Date - 21-12-2021 |  |  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20
Building Element | Maintainence Required | Notes | Information Source | Recommended Option | Alternative Option | 2021-07-01 | 2022-07-01 | 2023-07-01 | 2024-07-01 | 2025-07-01 | 2026-07-01 | 2027-07-01 | 2028-07-01 | 2029-07-01 | 2030-07-01 | 2031-07-01 | 2032-07-01 | 2033-07-01 | 2034-07-01 | 2035-07-01 | 2036-07-01 | 2037-07-01 | 2038-07-01 | 2039-07-01 | 2040-07-01
Asbestos | Repair | Asbestos Register - Assume asbestos - Lino, switchboard | Asbestos Register - Laserfiche | No work needed unless work is carried out on these specific areas
Roof | Paint | Corrugated roof requires painting | Inspection | Pressure wash roof and repaint including roof edge protection - repaint evey 8 years |  | 2023-07-01: 10000; 2031-07-01: 15000; 2039-07-01: 20000
| Repair | Brick chimney and loose nails to corrugated iron | Inspection | Lower brick chimney to below roof level and patch roof to be completed at the same time as the roof painting so the same roof edge protection can be used |  | 2023-07-01: 5000
|  |  |  | Remove all nails and replace with roofing screws to be done at the same time as roof painting so the same roof edge protection can be used |  | 2023-07-01: 2000
Replace
Spouting & Downpipes and Drainage | Clean | Spouting needs cleaning | Inspection | Clean spouting every year |  | 150 | 150 | 150 | 200 | 200 | 200 | 200 | 250 | 250 | 250 | 300 | 300 | 300 | 350 | 350 | 350 | 350 | 400 | 400 | 400
Repair
| Replace | No stormwater control - discharges to ground | Inspection and discussion with drainlayer | Low soakage in the Hawarden area - sugguest oversized inground soak pit |  | 2023-07-01: 2500
Exterior Cladding | Paint | Weatherboard - areas of primed weatherboards which have not been top coated - exterior requires painting in cluding the cedar shingles to the gable end | Inspection | Repaint exterior of the building - then repaint every 8yrs |  | 2023-07-01: 12000; 2031-07-01: 17000; 2039-07-01: 22000
| Repair | Cracks to the ring foundation - rumble foundation | Inspection | Epoxy grout the cracks and paint over |  | 2023-07-01: 1000
Replace
Bathroom, W/C & Laundry | Repair | w/c pan and cistern have been replaced - no hand basin for the w/c - kitchette sink is currently being used | Inspection | Install wash hand basin in the w/c area - this work would require either a building consent or an Exemption |  | 2023-07-01: 3000
Replace
Kitchen | Repair
| Replace | Very old laminate bench top and timber cabinets below - poor condition Old Zip water heater (Asbestos?) | Inspection | Replace bench top and cabinets below - remove water heater |  | 2023-07-01: 5000
Flooring | Repair
| Replace | New commercial vinyl to the w/c area. Old lino (asbestos ??) | Inspection | Remove old lino and dispose Lay new commercial carpet tiles 50m2 | Remove old lino and dispose Lay new commercial vinyl | 2023-07-01: 6000
Windows & Doors | Paint
| Repair | Door into the kitchen are rubs on the lino | Inspection | Ease door |  | 2021-07-01: 100
Replace
Interior Walls & Ceilings | Paint | The interior walls and ceilings are in reasonable condition but have not been painted in a long time | Inspection | Repaint walls and ceilings and then every 8 yrs thereafter |  | 2023-07-01: 7000; 2031-07-01: 9000; 2039-07-01: 11000
Repair
Replace
Facilities and Disabled | Repair | There are no accessible facilities in this building | Inspection
Replace
Total Costs | [5 empty] | 250 | 150 | 53650 | 200 | 200 | 200 | 200 | 250 | 250 | 250 | 41300 | 300 | 300 | 350 | 350 | 350 | 350 | 400 | 53400 | 400
[6 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20
Note - If any work is carried out which requires a building consent then there may be a requirement to upgrade facilities for accessibility

## Hawarden Community Hall
Hawarden Community War Memorial Hall
PROP 1148 (1148-Hall)
Condition Inspection Date - 15-12-2021 | [5 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20
Building Element | Maintainence Required | Notes | Information Source | Recommended Option | Alternative Option | 2021-07-01 | 2022-07-01 | 2023-07-01 | 2024-07-01 | 2025-07-01 | 2026-07-01 | 2027-07-01 | 2028-07-01 | 2029-07-01 | 2030-07-01 | 2031-07-01 | 2032-07-01 | 2033-07-01 | 2034-07-01 | 2035-07-01 | 2036-07-01 | 2037-07-01 | 2038-07-01 | 2039-07-01 | 2040-07-01
Asbestos | Repair | There are various areas identified as having asbestos present eg electrical switch boards, vinyl etc The cladding on the lean to gable is cracked and crumbling | Asbestos Register | Remove the cladding and replace, and paint As for the remaining asbestos no immediate action is required as the asbestos is all contained |  | 2021-07-01: 1500
Roof | Paint | Currently the roof is painted galvanised iron - areas of corrision which could be spot treated, paint is either peeling or worn off | Inspection | Pressure wash, spot prime any corrision or bare metal - repaint entire roof including roof edge protection |  | 2023-07-01: 23000
|  | Repaint corrugated roofing every 8yrs |  |  | Replace corrugate roofing with colorsteel -$45000.00 - | 2031-07-01: 15000
| Repair | Loose nails, some small holes and tears to the iron | Inspection | Remove existing nails and replace with roofing screws. Completed at same time as roof paint to enable the use of the roof edge protection |  | 2023-07-01: 3000
| Replace | Flat roof area - badly corroded with poor junction detailing approx 35m2 | Inspection | Replace flat roof area on the east end of the building - ply substrate and butynol membrane as some of the corrugate iron will neeed to be removed for this repair - replace any torn sheets |  | 2023-07-01: 35000
Spouting & Downpipes | Clean | Clean gutters yearly | Inspection | Clean gutters every year |  | 2021-07-01: 200; 2022-07-01: 200; 2023-07-01: 200; 2024-07-01: 200; 2025-07-01: 250; 2026-07-01: 250; 2027-07-01: 250; 2028-07-01: 250; 2029-07-01: 300; 2030-07-01: 300
| Repair | Some gutter brackets are broken | Inspection | Replace broken brackets |  | 2023-07-01: 500
Replace
Exterior Cladding | Paint | The exterior of the building is in need of a complete repaint | Inspection | Repaint exterior of building once the blockwork to the cloakroom has been seismically strengthened. Paint exterior using an elastomeric paint system - which will bridge any small cracks to to blockwork and stucco EG Dulux Acratex Then every 8yrs after that |  | 2023-07-01: 20000; 2031-07-01: 35000
| Repair | The building is deemed as below 33% NBS. There is an Engineers Design to strengthen the cloakroom area There is separate budget for this. | DSA report by Elliott Sinclair 11-11-2020
|  | Minor cracks to the stucco are superfical | Inspection | These cracks are minor - fill with MS sealant and paint - included with exterior painting
|  | Damage to external corner of stucco south east corner | Inspection | Grind back and re plaster |  | 2023-07-01: 500
| Replace | Cracked cement board already allowed for in the asbestos heading | Inspection
Bathroom, W/C & Laundry | Repair
| Replace | W/C area is below standard - end of life cycle for the fittings and fixtures | Inspection | Replace fixtures and fittings |  | 2023-07-01: 15000
Kitchen | Repair
| Replace | Laminate bench top has been scorched | Inspection | Replace laminate bench top |  | 2023-07-01: 1500
Flooring | Repair | Polished floor is in resonable condition but will require a light sand and re finishing | Inspection | Sand and refinish approximate 330m2 light sand only as the floor boards are thin and will not stand heavy sanding |  | 2023-07-01: 10000; 2028-07-01: 5000
| Repair | Painted floor to w/c area - peeling |  | Grind back and repaint |  | 2023-07-01: 1500
| Replace | Vinyl is in reasonable condition but is dated particulaily in the committee room - Vinyl has been identified as containing asbestos | Inspection | Replace vinyl with vinyl plank (if a plank is damaged then this can be lifted and replaced ) | Leave until completely worn out | 2023-07-01: 3000
Windows & Doors | Paint | Flakey paint, rot | Inspection | Included in the exterior painting
| Repair | Some sills have been repaired already and the repair covered with sheet metal without taking of the metal cover it is very hard to determine the extent of the rot -assume rotten under the sheet metal | Inspection | Replace windows which have rotten sills with aluminium joinery $10,000.00 | Replace all window joinery with aluminium joinery including front doors - $40000.00 | 2023-07-01: 10000
Remove sheet metal and repair sills - $5000
| Repair | Various doors need to be eased and hardware replaced | Inspection |  |  | 2023-07-01: 1000
Replace
Interior Walls & Ceilings | Paint | Ceiling tiles are dirty and discoloured the w/c walls have never been painted and so are not easily cleaned or impervious | Inspection | Paint interior of building - repaint every 8 yrs |  | 2023-07-01: 20000; 2031-07-01: 25000
Repair
| Replace | Ceilings in the w/c's are damaged and need replacing | Inspection |  |  | 2023-07-01: 4000
Electrical | Inspection | Sugguest an electrical safety inpection | Inspection | Electrical safety inspection |  | 2021-07-01: 500
| Replace | Heaters in hall and committee room old , inefficent and have scorched the ceiling | Inspection | Hi Wall - heat pump to the committee room and ceiling cassette heat pumps x 3 to main hall in the ceiling grid - $25000 | Replace the existing wall heaters with new wall mounted heaters $10000 | 2023-07-01: 10000
Facilities and Disabled | Repair | Depending on building consent requirements | Inspection | Maybe some signage upgrades , mark carpark for example . Allow say $1000.00 |  | 2023-07-01: 1000
Total Costs | [5 empty] | 2200 | 200 | 159200 | 200 | 250 | 250 | 250 | 5250 | 300 | 300 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20

## Waikari Hall
Waikari Memorial Hall
PROP1165
Condition Inspection carried out - 20-10-2021 | [5 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20
Building Element | Maintainence Required | Notes | Information Source | Recommended Option | Alternative Option | 2021-07-01 | 2022-07-01 | 2023-07-01 | 2024-07-01 | 2025-07-01 | 2026-07-01 | 2027-07-01 | 2028-07-01 | 2029-07-01 | 2030-07-01 | 2031-07-01 | 2032-07-01 | 2033-07-01 | 2034-07-01 | 2035-07-01 | 2036-07-01 | 2037-07-01 | 2038-07-01 | 2039-07-01 | 2040-07-01
Asbestos | Repair | Asbestos identified on the register - Mainly switchboards and textured ceilings | Asbestos Register oin Laserfische | Low risk - keep contained - form a management plan prior to any work being carried out in these areas
Roof | Paint | Roof paint fading | Inspection | Repaint including edge protection and then every 8 yrs there after |  | 2023-07-01: 20000; 2031-07-01: 25000; 2039-07-01: 30000
| Repair | Loose nails - minimal | Inspection | Replace loose nails with roofing screws |  | 2023-07-01: 500
|  | Dodgey flashing by the roadside parapet | Inspection | Repair flashing |  | 2023-07-01: 500
|  | Toilet block has seperated slighly from the main hall - noticable on the north elevation - pulling the apron flashing away from the wall allowing water entry | Inspection | This could be included with the earthquake work
Replace
Spouting & Downpipes | Clean | Clean out spouting at regular intervals | Inspection | Clean yearly |  | 2021-07-01: 200; 2022-07-01: 200; 2023-07-01: 200; 2024-07-01: 200; 2025-07-01: 250; 2026-07-01: 250; 2027-07-01: 250; 2028-07-01: 300; 2029-07-01: 300; 2030-07-01: 300
Repair
| Replace | Spouting and downpipes are in poor condition | Inspection | Replace spouting and downpipes |  | 2023-07-01: 2000
Exterior Cladding | Paint | Repainting required - To be completed once earthquake stregthening has been completed | Inspection | Repaint exterior of building once the building has been seismically strengthened. Paint exterior using an elastomeric paint system - which will bridge any small cracks to to blockwork and stucco EG Dulux Acratex Then every 8yrs after that |  | 2023-07-01: 25000; 2031-07-01: 30000; 2039-07-01: 35000
| Repair | Toilet block has seperated slighly from the main hall - noticable on the north elevation | Inspection | This could be included with the earthquake work
Replace
Bathroom, W/C & Laundry | Repair
| Replace | W/C area is below standard - end of life cycle for the fittings and fixtures | Inspection | Replace fixtures and fittings |  | 2023-07-01: 15000
Kitchen | Repair | Cupboaard doors out of alignment | Inspection | Adjust doors and drawers |  | 2023-07-01: 100
Replace
Flooring | Repair | Borer in floor between room dividers - flooring could give way when walked on | Inspection | Repair floor and re poly |  | 2021-07-01: 1000
|  | Refinish timber floor areas - Apprximate 400m2 based on quote for Amberley Pavillion - $65m2 - $26000.00 plus GST This floor has no sports court markings so the m2 rate will be less - so allow $50m2 | Inspection - will need to be looked at by flooring contractor | Have floor surface looked at by flooring contractor and then decide plan of refinish - Approximate 400m2 | Note - the floor will need to be cut to allow for the excavations for the earthquake strengthening so the cost of the floor refinish maybe included with the earthquake strenthening budget | 2023-07-01: 20000; 2028-07-01: 6000; 2033-07-01: 7000; 2038-07-01: 8000
| Replace | Cracked tiles to front steps and entrance | Inspection | Remove and replace |  | 2023-07-01: 1500
Windows & Doors | Paint
| Repair | Womans toilet lobby door doesn’t close | Inspection | Repair |  | 2023-07-01: 150
|  | Kitchen door to front dining room doesn’t close | Inspection | Repair |  | 2023-07-01: 150
|  | Lobby to hall doors rub on the floor | Inspection | Ease doors |  | 2023-07-01: 150
|  | Door to stage doesn’t latch | Inspection | Repair latch |  | 2023-07-01: 150
| Replace | Double doors from dining to the exterior are rotten | Inspection | Replace doors and reuse crash bar hardware |  | 2021-07-01: 2000
|  | Side door from small dining to exterior delaminating | Inspection | Replace door and hardware |  | 2021-07-01: 1500
|  | Exterior door from kitchen delaminating | Inspection | Replace door and hardware |  | 2021-07-01: 1500
|  | Tower bolt is broken on the double doors to the main hall | Inspection | Replace tower bolt |  | 2021-07-01: 500
|  | Broken window hardware | Inspection | Replace |  | 2023-07-01: 750
Interior Walls & Ceilings | Paint | Kitchen walls have bubbled paint from water damage or poor surface preparation- Any leaks appear to have been fixed | Inspection | Repaint kitchen area
|  | Womans toilets bubbling paint | Inspection | Repaint affected toilet walls
|  | Front entance lobby | Inspection | Paint after repairs
|  | Repaint to the entire interior | Inspection | Repaint to include the above areas mentioned |  | 2023-07-01: 30000; 2031-07-01: 35000; 2039-07-01: 40000
| Repair | Skirting coming away from walls in main hall | Inspection | Re fix skirting |  | 2023-07-01: 200
|  | Scotia coming away from the ceiling in the dining room | Inspection | Re fix moulding |  | 2023-07-01: 100
| Replace | Cracking to lath and plaster in the entrance lobby and to the rhs of the stage | Inspection | Remove lath and plaster - re line and plaster |  | 2023-07-01: 3000
Facilities and Disabled | Repair | There are no facilities for disabled - some upgrade to accessible facilities may be required when a building consent is applied for the strengthening work
Replace
Total Costs | [5 empty] | 6700 | 200 | 119450 | 200 | 250 | 250 | 250 | 6300 | 300 | 300 | 90000 | 0 | 7000 | 0 | 0 | 0 | 0 | 8000 | 105000 | 0
[6 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20